## Sheet1
Task | Start Date | Days to Complete
Global Components / Style | 2018-09-26 | 7
Frontend Page Components | 2018-10-01 | 15
Frontend QA | 2018-10-13 | 4
Database User Accounts Setup | 2018-10-15 | 10
User Interaction / Lookup | 2018-10-21 | 7
Setup Group DB Table | 2018-10-26 | 4
Group Creation by Users | 2018-10-31 | 7
Realtime Chat Server | 2018-11-07 | 5
Tasks Setup within Groups | 2018-11-10 | 12
Search for Issues / Bugs | 2018-11-26 | 8